## Task List
Week # | Task # | Task Description | Estimated Time (Hours) | Member Responsible
7 | 1 | Finalise and submit project proposal | 5 | Bharath
8 | 1 | Set up Python/Streamlit development environment | 2 | Bharath
8 | 2 | Download and explore AISHELL-1 corpus | 2 | Bharath | Total Hours | 104
8 | 3 | Write scripts to extract tone-labelled audio segments from AISHELL-1 | 3 | Bharath
8 | 4 | Verify access to Bu et al. (2025) corpus; pursue alternative if unavailable | 1 | Bharath | Bharath | 104
8 | 5 | Pre-extract native speaker reference pitch contours using Parselmouth | 2 | Bharath
9 | 1 | Extract F0-based acoustic features from AISHELL-1 training set | 3 | Bharath
9 | 2 | Train and evaluate SVM/feedforward classifier on T1-T4 | 4 | Bharath
9 | 3 | Generate confusion matrix and per-class F1 scores | 2 | Bharath
9 | 4 | Iterate on feature engineering to improve classification accuracy | 2 | Bharath
9 | 5 | Write Weekly Status Check 2 | 2 | Bharath
10 | 1 | Build Streamlit audio recording interface | 3 | Bharath
10 | 2 | Integrate Parselmouth pitch extraction into recording pipeline | 2 | Bharath
10 | 3 | Implement pitch contour overlay visualisation (learner vs. native reference) | 3 | Bharath
10 | 4 | Connect tone classifier to interface for end-to-end demo | 2 | Bharath
10 | 5 | Finalise monosyllabic word list | 1 | Bharath
10 | 6 | Prepare and submit Intermediate Milestone 1 video | 2 | Bharath
10 | 7 | Write Weekly Status Check 3 | 2 | Bharath
INTERMEDIATE MILESTONE 1 DUE
11 | 1 | Write plain-language correction cues for all T1-T4 error combinations | 3 | Bharath
11 | 2 | Extend word list to disyllabic words including tone sandhi contexts | 2 | Bharath
11 | 3 | Integrate disyllabic words into interface | 2 | Bharath
11 | 4 | Refine UI layout and feedback display based on Milestone 1 feedback | 2 | Bharath
11 | 5 | Write Weekly Status Check 4 | 1 | Bharath
12 | 1 | Design pre/post tone perception test (20 audio clips each) | 3 | Bharath
12 | 2 | Develop TAM-based post-session usability survey | 2 | Bharath
12 | 3 | Prepare participant instructions and consent materials | 2 | Bharath
12 | 4 | Begin participant recruitment | 2 | Bharath
12 | 5 | Write Weekly Status Check 5 | 1 | Bharath
13 | 1 | Run evaluation sessions with 6-10 participants | 4 | Bharath
13 | 2 | Collect pre/post perception test scores and survey responses | 2 | Bharath
13 | 3 | Begin preliminary analysis of evaluation data | 3 | Bharath
13 | 4 | Prepare and submit Intermediate Milestone 2 video | 2 | Bharath
13 | 5 | Write Weekly Status Check 6 | 2 | Bharath
INTERMEDIATE MILESTONE 2 DUE
14 | 1 | Complete analysis of technical and learner evaluation results | 4 | Bharath
14 | 2 | Draft paper: Introduction, Related Work, Proposed Work sections | 5 | Bharath
14 | 3 | Write Weekly Status Check 7 | 2 | Bharath
15 | 1 | Draft and finalise paper: Results, Discussion, Limitations, Future Work | 5 | Bharath
15 | 2 | Revise and polish full paper draft | 3 | Bharath
15 | 3 | Prepare final presentation slides or recording | 2 | Bharath
15 | 4 | Write Weekly Status Check 8 | 2 | Bharath
16 | 1 | Final review and polish of tool, paper, and presentation | 2 | Bharath
16 | 2 | Deploy tool to Streamlit Community Cloud | 1 | Bharath
16 | 3 | Ensure GitHub repository is clean and documented | 1 | Bharath
16 | 4 | Submit project, paper, and presentation | 1 | Bharath
FINAL PROJECT DUE
Note on A1: The week of the semester, from week 8 to week 16.
Note on B1: An identifer for each task. This is just used for easier conversation, e.g. "It looks like you didn't finish Task 5."
Note on C1: A brief (~1 sentence or fragment) description of the task.
Note on D1: The estimated number of hours to complete the task.
Note on E1: For team projects, which team member is responsible for the task.
Note on G6: Names of the team members can be placed here to auto-sum their portions.